# Appendix C: PPOST- All Hazards Action Planning Tool

When faced with a complex incident where the community may not have a “Hazard Specific Plan” developing a PPOST is a way to think things through and formulate a plan.

Gather your Local EMO and walk through identifying priorities, problems, objectives, strategies and tactics under their titles in the table below (see example):

| Scenario: Wildfire is close to small NWT community but not yet a significant threat. Residents and the community needs to be prepared for potential evacuation. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Priorities What are the important items to prioritize? See NWT Emergency Plan for standard list of priorities. | Problems What does the Local EMO know and observe about the incident? | Objectives What is the Local EMO going to do? S: Specific M: Measurable A: Action-Oriented R: Realistic T: Time Specific | Strategies How is the Local EMO going to get it done? By what method? | Tactics With what resources? |
| Save lives / ensure public safety | A wildfire nearby may pose an eventual threat to community residents | Make sure all evacuation preparations are in place within 48 hours. | Local Coordinator to call for Local EMO meeting to inform and assign tasks. | At the band office boardroom (EOC) at 10am. |
|  |  |  | Pre-register all residents using registration template in Appendix I to gather evacuee data (how many people need transportation, hosting, medical care or other special considerations) by 6pm. | Door-to-door registration carried out by Fire Department volunteers and Municipal Works crew using paper registration forms. |
|  |  |  | Tally up resident pre-registration results by 8pm to better understand who needs what kind of assistance. | Local EMO members to gather pre-registration forms and create chart summarizing support requests. |
|  |  |  | Joe (Local EMO member) to put plans in place for all residents identifying they need help with evacuation transportation by 10am. | See if there are volunteers to help carpool, or arrange for a bus to be available. |
|  |  |  | Mike (Local Coordinator) to work with Regional EMO to identify the potential request assistance to the Regional EMO should there be a need to evacuate by air by 10am. | Call the Regional EMO and follow up with a Request for Assistance Form. |
|  |  |  | Barb (Local EMO member) to inform/update residents about evacuation protocols and update by noon. | Door-to-door notification by Fire Department and SAO to post on the community government’s website or social media page. |
|  |  |  | Mike (Local Coordinator) to work with MACA and ENR to determine when to send evacuation order out to residents (what is the trigger point?) | Daily phone calls at 10am. |